## Sheet1
|  |  | 06.10.14 |  |  |  |  | 13.10.14 |  |  |  |  | 20.10.14 |  |  |  |  | 27.10.14 |  |  |  |  | 03.11.14 |  |  |  |  | 10.11.14 |  |  |  |  | 17.11.14 |  |  |  |  | 24.11.14 |  |  |  |  | 01.12.14 |  |  |  |  | 08.12.14
|  |  | Week2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11
No | Task | Duration | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Design Assignment Brief page | 10
1.1 | Familiarise with Brief | 2
1.2 | Skills Audit | 2
1.3 | Implement brief web page | 6
1.4 | Finalise Brief | 2
2 | Design web site mockup | 5
2.1 | Use case diagrams | 2
2.2 | Sequence diagrams | 2
2.3 | Class diagrams | 3
3 | Implement web site | 15
3.1 | Database and other back end | 3
3.2 | Log in/ Register | 2
3.3 | Services | 9
3.3.1 | Open Account | 3
3.3.2 | Transfer Money | 3
3.3.3 | View Accounts | 3
3.3.4 | View Statements | 3
3.4 | Admin page | 3
3.5 | Finalise pages | 2
4 | Testing and Refinement | 10
4.1 | White Box Testing | 4
4.2 | Black Box Testing | 4
4.3 | User acceptance testing | 4
4.4 | Top level tests | 4
4.5 | Refinement | 5
5 | Create Technical Manual | 5
5.1 | Tools and technologies discussion | 2
5.2 | Technical Features of Web App | 2
5.3 | Finalise Technical Manual | 3
6 | Create User Manual | 5
6.1 | Describe how the web app works | 4
6.2 | Include multimedia information | 2
Indicates deadline:
17.10.14 Assignment Brief Web page
09.12.14 Web App and Manuals Submission